## Ark1
Tidsregistrering af (Navn)
Opgavebeskrivelse | Rolle | Dato | Starttid (i timer) | Sluttid (i timer) | Estimeret tidsforbrug | Aktuelt tidforbrug (i timer) | Timer i alt
Opdelt tjekliste i deres seperate emner sammen med tommy | Review Cordinator | 2020-02-24 | 9:30 | 10:20 | 30 minutter | 0:50 | 0:50
Review af vision doc | Reviewer | 2020-02-24 | 11:00 | 11:30 | 30 minutter | 0:30 | 1:20
Ændrede use case 1 da vi havde problemer med vores mockup | Requirement Specifier | 2020-02-24 | 12:00 | 13:00 | 10 minutter | 1:00 | 2:20
Begyndte på mockup med Emil N. til android app | Graphic artist | 2020-02-24 | 13:00 | 16:00 | 2 timer | 3:00 | 5:20
Viderearbejde med mockup til android app | Graphic artist | 2020-02-25 | 8:40 | 11:00 | 2 timer | 2:20 | 7:40
Start på mockup til desktop | Graphic artist | 2020-02-25 | 12:20 | 13:30 | 1 timer | 1:10 | 8:50
Lavet OC0101 med Emil | System Analyst | 2020-02-25 | 13:40 | 14:20 | 1 timer | 0:40 | 9:30
Ret OC0101 med emil | System Analyst | 2020-02-25 | 15:20 | 15:30 | 10 minutter | 0:10 | 9:40
Review af OC0103 | Reviewer | 2020-02-25 | 15:30 | 16:00 | 30 minutter | 0:30 | 10:10
blev klogere på løsningen af mine næste opgaver | Requirement Specifier | 2020-02-26 | 9:00 | 10:30 | 1 timer | 1:30 | 11:40
Snakked med høk for at lave AD02, DD02 og Mockup | Requirement Specifier | 2020-02-26 | 10:30 | 11:50 | 1,5 time | 1:20 | 13:00
Brugertest på høk | User-Interface Designer | 2020-02-26 | 12:30 | 13:20 | 1time | 0:50 | 13:50
Produceret AD02 og DD02 | Requirement Specifier | 2020-02-26 | 13:30 | 14:35 | 1 timer | 1:05 | 14:55
Start på review af UC06 | Reviewer | 2020-02-27 | 8:30 | 9:00 | 10 minutter | 0:30 | 15:25
Rettelse af Mockup til desktop | Graphic artist | 2020-02-27 | 9:00 | 11:20 | 1 timer | 2:20 | 17:45
Vi skulle lave design alle sammen | Designer | 2020-02-27 | 12:30 | 16:00 | 4 timer | 3:30 | 21:15
Review af UC04 | Reviewer | 2020-02-28 | 9:00 | 9:30 | 30 minutter | 0:30 | 21:45
Rettelse af SSD08 | System Analyst | 2020-02-28 | 9:30 | 12:10 | 1 timer | 2:40 | 24:25
SD0101 | Software architect | 2020-02-28 | 13:00 | 14:00 | 1 timer | 1:00 | 25:25
SD og DCD 0103 | Software architect | 2020-03-02 | 9:00 | 11:00 | 2 timer | 2:00 | 27:25
review af sd0804 | Reviewer | 2020-03-02 | 11:35 | 11:55 | 10 minutter | 0:20 | 27:45
review af sd0804 | Reviewer | 2020-03-02 | 12:30 | 12:50 | 10 | 0:20 | 28:05
implementering af SD0103 | Implenter | 2020-03-02 | 13:00 | 14:00 | 1 timer | 1:00 | 29:05
implementering af SD0104 med Sune | Implenter | 2020-03-02 | 14:00 | 15:00 | 1 timer | 1:00 | 30:05
Review af UC07 | Reviewer | 2020-03-03 | 9:00 | 9:30 | 30 minutter | 0:30 | 30:35
SD0804 0g og OC0802 | Software architect | 2020-03-03 | 11:00 | 15:00 | 2 timer | 4:00 | 34:35
Fællessnak om chain of responsibility | Software architect | 2020-03-04 | 9:00 | 10:00 | 1 timer | 1:00 | 35:35
SD0804 og DCD08 | Software architect | 2020-03-04 | 10:30 | 13:00 | 1 timer | 2:30 | 38:05
Kundemøde om DD12, AD12 og ATD12b | Requirement Specifier | 2020-03-04 | 14:00 | 16:00 | 1 timer | 2:00 | 40:05
Lavede atd12 og kiggede på DD12 og AD12 med daniel | Test Analyst | 2020-03-05 | 8:30 | 9:30 | 30 minutter | 1:00 | 41:05
ret UCD01 | Requirement Specifier | 2020-03-05 | 9:55 | 10:30 | 30 minutter | 0:35 | 41:40
review af Sunes guide til merge conflict | Reviewer | 2020-03-05 | 10:30 | 10:50 | 10 minutter | 0:20 | 42:00
implementer 0802 | Implenter | 2020-03-05 | 12:00 | 16:00 | 3 timer | 4:00 | 46:00
implementer 0802 | Implenter | 2020-03-06 | 9:00 | 13:30 | 2 timer | 4:30 | 50:30
review af ATD04 | Reviewer | 2020-03-06 | 13:30 | 13:40 | 10 minutter | 0:10 | 50:40
[6 empty] | 0:00 | 50:40
[6 empty] | 0:00 | 50:40
[6 empty] | 0:00 | 50:40
[6 empty] | 0:00 | 50:40
[6 empty] | 0:00 | 50:40
[6 empty] | 0:00 | 50:40
[6 empty] | 0:00 | 50:40
[6 empty] | 0:00 | 50:40
[6 empty] | 0:00 | 50:40
[6 empty] | 0:00 | 50:40
[6 empty] | 0:00 | 50:40
[6 empty] | 0:00 | 50:40

## Ark2
Roller!
ID | Navn
1 | business-Process Analyst
2 | business designer
3 | System Analyst
4 | Requirement Specifier
6 | Software Architect
7 | Designer
8 | User-Interface Designer
9 | Capsule Designer
10 | Implenter
11 | integrator
12 | Project Manager
13 | Change Control Manager
14 | Configuration Manager
15 | Test Manager
16 | Deployment Manager
17 | Process Engineer
18 | Management Reviewer
19 | Test Analyst
20 | Test Desinger
21 | Tester
22 | System Adminstrator
23 | Techincal Writer
24 | Graphic Artist
25 | Tool Specialist
26 | Course Developer
27 | Reviewer
28 | Review Cordinator
29 | Any Role
30 | Stakeholders