## Ark1
Tidsregistrering af (Navn)
Opgavebeskrivelse | Rolle | Dato | Starttid (i timer) | Sluttid (i timer) | Estimeret tidsforbrug | Aktuelt tidforbrug (i timer) | Timer i alt
Renskriv UC01 | Requirement Specifier | 2020-02-24 | 9:30 | 10:30 | 1 | 1:00 | 1:00
Krydscheck UC01, AD01 og DOM01 | Requirement Specifier | 2020-02-24 | 13:00 | 15:00 | 2 | 2:00 | 3:00
Ret i UC08 | Requirement Specifier | 2020-02-25 | 9:00 | 12:00 | 1 | 3:00 | 6:00
Lav SSD08 beregn afsætning | System Analyst | 2020-02-25 | 12:30 | 14:30 | 1 | 2:00 | 8:00
Lav OC0104 | System Analyst | 2020-02-25 | 14:30 | 16:10 | 2 | 1:40 | 9:40
Lav AD02 | Requirement Specifier | 2020-02-26 | 11:00 | 12:00 | 1:30 | 1:00 | 10:40
Lav DD02 | Requirement Specifier | 2020-02-26 | 11:00 | 14:00 | 1:30 | 3:00 | 13:40
Brugertest | User-Interface Designer | 2020-02-26 | 12:30 | 14:00 | 1 | 1:30 | 15:10
Brugertest opgaver opdateret til UC01 og UC08 | User-Interface Designer | 2020-02-27 | 9:00 | 10:00 | 1 | 1:00 | 16:10
oc0804 er reviewet | Reviewer | 2020-02-27 | 10:00 | 11:00 | 0:30 | 1:00 | 17:10
Krydscheck UC02, AD02 og DOM02 | Reviewer | 2020-02-28 | 9:00 | 11:00 | 1 | 2:00 | 19:10
Lav SD0102 og DCD0102 | Designer | 2020-02-28 | 11:30 | 14:00 | 2 | 2:30 | 21:40
Lav SD0801 | Designer | 2020-02-29 | 9:00 | 14:00 | 4 | 5:00 | 26:40
UC01 UI implementering | Implenter | 2020-02-29 | 14:00 | 15:00 | 3 | 1:00 | 27:40
UC01 UI implementering | Implenter | 2020-03-03 | 9:00 | 13:00 | 3 | 4:00 | 31:40
Review af UT og UTD 05 og 06 | Reviewer | 2020-03-03 | 13:30 | 14:15 | 0:30 | 0:45 | 32:25
Undersøg javafx og gradle | Software Architect | 2020-03-03 | 14:15 | 16:00 | 5 | 1:45 | 34:10
Tilføj Gradle funktionalitet | Software Architect | 2020-03-04 | 9:00 | 11:00 | 2 | 2:00 | 36:10
Review af UT sunes | Reviewer | 2020-03-04 | 12:30 | 13:00 | 0:30 | 0:30 | 36:40
Lav UC12, DOM12, ATD12 | Requirement Specifier | 2020-03-04 | 14:15 | 15:40 | 3 | 1:25 | 38:05
[6 empty] | 0:00 | 38:05
[6 empty] | 0:00 | 38:05
[6 empty] | 0:00 | 38:05
[6 empty] | 0:00 | 38:05
[6 empty] | 0:00 | 38:05
[6 empty] | 0:00 | 38:05
[6 empty] | 0:00 | 38:05
[6 empty] | 0:00 | 38:05
[6 empty] | 0:00 | 38:05
[6 empty] | 0:00 | 38:05

## Ark2
Roller!
ID | Navn
1 | business-Process Analyst
2 | business designer
3 | System Analyst
4 | Requirement Specifier
6 | Software Architect
7 | Designer
8 | User-Interface Designer
9 | Capsule Designer
10 | Implenter
11 | integrator
12 | Project Manager
13 | Change Control Manager
14 | Configuration Manager
15 | Test Manager
16 | Deployment Manager
17 | Process Engineer
18 | Management Reviewer
19 | Test Analyst
20 | Test Desinger
21 | Tester
22 | System Adminstrator
23 | Techincal Writer
24 | Graphic Artist
25 | Tool Specialist
26 | Course Developer
27 | Reviewer
28 | Review Cordinator
29 | Any Role
30 | Stakeholders