## Ark1
Tidsregistrering af Marc
Opgavebeskrivelse | Rolle | Dato | Starttid (i timer) | Sluttid (i timer) | Estimeret tidsforbrug | Aktuelt tidforbrug (i timer) | Timer i alt
UT01 - Brugertest af UC01 og UC08 |  | 2020-02-25 | 9:15 | 11:15 | 2 timer | 2:00 | 2:00
UI-prototype android | reviewer | 2020-02-25 | 12:20 | 12:30 | 10 til 20 min | 0:10 | 2:10
UI-prototype desktop | reviewer | 2020-02-25 | 13:40 | 13:50 | 10 til 20 min | 0:10 | 2:20
OC0103 - angiv primo | System Analyst | 2020-02-25 | 14:00 | 15:10 | 1 time | 1:10 | 3:30
OC0802 angivBrugstidogScrapværdiogAnskaffelseværd | System Analyst | 2020-02-26 | 9:30 | 10:10 | 30 min | 0:40 | 4:10
Kundemøde KKO |  | 2020-02-26 | 11:15 | 11:55 | 45min | 0:40 | 4:50
Kundemøde Indtjeningsbidrag |  | 2020-02-26 | 12:40 | 13:20 | 45min | 0:40 | 5:30
OC06 beregn kontant kapacitetomkostning | System Analyst | 2020-02-26 | 13:30 | 14:05 | 30min | 0:35 | 6:05
AD07 beregn indtjeningsbidrag |  | 2020-02-27 | 8:45 | 9:38 | 1 time | 0:53 | 6:58
Review UC02 | reviewer | 2020-02-27 | 9:50 | 10:00 | 10 til 20 min | 0:10 | 7:08
review DOM02 | reviewer | 2020-02-27 | 10:00 | 10:12 | 10 til 20 min | 0:12 | 7:20
Rette OC06 | System Analyst | 2020-02-28 | 8:45 | 8:55 | 10min | 0:10 | 7:30
ATD07b |  | 2020-02-28 | 9:00 | 9:30 | 30 min | 0:30 | 8:00
ATD06a |  | 2020-02-28 | 9:45 | 10:15 | 30 min | 0:30 | 8:30
DD07 |  | 2020-02-28 | 10:20 | 10:45 | 20 min | 0:25 | 8:55
lav SD0801 + DCD0801 | Designer | 2020-03-02 | 9:00 | 14:00 |  | 5:00 | 13:55
lav UI til UC01 |  | 2020-03-02 | 14:00 | 15:00 |  | 1:00 | 14:55
[6 empty] | 0:00 | 14:55
[6 empty] | 0:00 | 14:55
[6 empty] | 0:00 | 14:55
[6 empty] | 0:00 | 14:55
[6 empty] | 0:00 | 14:55
[6 empty] | 0:00 | 14:55
[6 empty] | 0:00 | 14:55
[6 empty] | 0:00 | 14:55
[6 empty] | 0:00 | 14:55
[6 empty] | 0:00 | 14:55
[6 empty] | 0:00 | 14:55
[6 empty] | 0:00 | 14:55
[6 empty] | 0:00 | 14:55

## Ark2
Roller!
ID | Navn
1 | business-Process Analyst
2 | business designer
3 | System Analyst
4 | Requirement Specifier
6 | Software Architect
7 | Designer
8 | User-Interface Designer
9 | Capsule Designer
10 | Implenter
11 | integrator
12 | Project Manager
13 | Change Control Manager
14 | Configuration Manager
15 | Test Manager
16 | Deployment Manager
17 | Process Engineer
18 | Management Reviewer
19 | Test Analyst
20 | Test Desinger
21 | Tester
22 | System Adminstrator
23 | Techincal Writer
24 | Graphic Artist
25 | Tool Specialist
26 | Course Developer
27 | Reviewer
28 | Review Cordinator
29 | Any Role
30 | Stakeholders